

Request for Proposal

40th EFFoST International Conference 2026

The European Federation of Food Science and Technology
Agro Business Park 82

6708 PW Wageningen
The Netherlands

EFFoST Managing Director
Gabriela Versteeg

tel: +31 88 3663 700
E-mail: info@effost.org

Table of Contents

[Summary 5](#_Toc98862739)

[1. Introducing EFFoST 6](#_Toc98862740)

[2. Introducing the EFFoST International Conference 7](#_Toc98862741)

[2.1 Conference aim and objectives 7](#_Toc98862742)

[2.2. Recent and future conferences 8](#_Toc98862743)

[3. Bid procedure 9](#_Toc98862744)

[3.1 Overview of the bid procedure 9](#_Toc98862745)

[3.2 Local Conference Committee (LOC) requirements 10](#_Toc98862746)

[3.3 Venue and Destination requirements 10](#_Toc98862747)

[4. Conference Specifications 11](#_Toc98862748)

[4.1 Conference structure 11](#_Toc98862749)

[4.2 Conference programme 12](#_Toc98862750)

[4.3 Conference timing 12](#_Toc98862751)

[**4.3.1**  **Frequency** 12](#_Toc98862752)

[**4.3.2**  **Period** 12](#_Toc98862753)

[**4.3.3**  **Duration** 13](#_Toc98862754)

[**4.3.4**  **Important dates** 13](#_Toc98862755)

[4.4 Other specifications 13](#_Toc98862756)

[5. Conference venue requirements 13](#_Toc98862757)

[5.1 Spatial requirements 13](#_Toc98862758)

[5.2 Technical requirements 14](#_Toc98862759)

[5.3 Catering 14](#_Toc98862760)

[6. Destination requirements 15](#_Toc98862761)

[6.1 Transportation 15](#_Toc98862762)

[6.2 Accommodation 15](#_Toc98862763)

[6.3 Social events 15](#_Toc98862764)

[6.4 Subvention 15](#_Toc98862765)

[7. EFFoST Conference Management 16](#_Toc98862766)

[**7.1 Local Organising Committee (LOC)** 16](#_Toc98862767)

[**7.2 EFFoST** 16](#_Toc98862768)

[**7.3 Scientific Committee (SC)** 16](#_Toc98862769)

[**7.4 Professional conference organizer (PCO)** 17](#_Toc98862770)

[**7.5 Conference Organising Committee (COC)** 17](#_Toc98862771)

[ANNEX I – Statistics of the EFFoST conference delegates 18](#_Toc98862772)

[ANNEX II - Expression of Interest 19](#_Toc98862773)

[ANNEX III – Roles and responsibilities of the LOC 22](#_Toc98862774)

[ANNEX IV – Roles and responsibilities of EFFoST 24](#_Toc98862775)

[ANNEX V – Roles and responsibilities of the Scientific Committee 26](#_Toc98862776)

[ANNEX VI – Roles and responsibilities of the PCO 26](#_Toc98862777)

[ANNEX VII – Roles and responsibilities of the COC 28](#_Toc98862778)

[Glossary 29](#_Toc98862779)

# **Summary**

The European Federation of Food Science and Technology (EFFoST) is pleased to open a call for proposals to host the 40th EFFoST International Conference to be held in 2026.

The bid process consists of two rounds. The first round requires interested [European affiliated organisations of EFFoST](https://effost.org/members/affiliated%2Borganisations/default.aspx) to submit an Expression of Interest to info@effost.org by **24 April 2023**. On **10 May 2023,** interested organisations will be invited to submit a full proposal before **12 June 2023**. In both rounds, information will be required by the prospective Local Organizing Committee (LOC), representing one or more Scientific Institutions related to food science and technology in their country. Candidate LOCs will be informed of the EFFoST Board’s decision in September.

This document provides detailed information and the requirements to submit a proposal.

Please find below an overview of the time line of the EFFoST Conference bid procedure, including important dates and deadlines.

|  |  |
| --- | --- |
| **Activity description**  | **Timeline** |
| Post Call for Expression of Interest on website and mail an invitation to bid, to societies and institutes in food science and technology and to Convention Bureaux and Congress centres | 13 March 2023 |
| Collect Expression of Interest | 24 April 2023 |
| Invitation to submit full proposal to bidders | 10 May 2023 |
| Collect full proposals | 12 June 2023 |
| Interview of bid and site visits | Jun– Aug 2023 |
| Inform Board of findings | 21 August 2023 |
| Select host and location for 40th EFFoST International Conference 2026 | EFFoST Board Meeting 4 Sept 2023 |
| EFFoST signs MoU with conference host | September - October 2023 |
| PCO signs contracts with conference venue and social event venues | October 2023 |

*Bid submission*

Written submissions should be sent to:

European Federation of Food Science and Technology

Att. Gabriela Versteeg

Via email: info@effost.org

Requests for further information or clarification of the requirements may be directed to the Managing Director of EFFoST, Gabriela Versteeg at g.versteeg@effost.org

Please note that we reserve the right to advise, at our discretion, all parties submitting a bid book, of further information/clarification of tender requirements resulting from any inquiry.

# **Introducing EFFoST**

The European Federation of Food Science and Technology (EFFoST) facilitates knowledge and technology exchange among food professionals. EFFoST creates opportunities for food scientists, engineers, technologists, policymakers and businesses in food and food-related areas to connect and collaborate with the objective to enhance the uptake of new technologies and developments. By supporting the advancement of food science and technology, EFFoST aims to accelerate the production of sustainable and healthy *food for all in a changing world*.

More than 130 societies, institutes and universities all over Europe are affiliated with the non-profit organisation EFFoST. We are Europe’s largest food science expert base and stakeholder group. EFFoST is the European group of the International Union of Food Science & Technology (IUFoST), which in turn is a full member of the International Council for Science (ICSU).

Our federation supports the further development of the field of food science and technology. There is a lot of expertise in microbiology, chemistry, physics, engineering, and other food-related disciplines. With joined forces, these disciplines can create more innovation, especially in cooperation with food producers. Our activities include science and technology communication as well as the dissemination of information and technology transfers. EFFoST puts additional emphasis on the involvement of SMEs and on fostering the next generation of food scientists and professionals. We also offer our knowledge and independent advice to the European Commission, so it can develop an effective strategic research agenda.

**Our vision** - Quality food for all in a changing global environment.

**Our mission** - In a world of changing climate, a growing population, reducing biodiversity, challenging supply chains, global health crises and social tensions, EFFoST will mobilise scientific knowledge, creativity, entrepreneurial spirits and sustainable innovation pathways to guarantee safe, healthy and appealing food for all.

**Our ambition:**

* To realise our mission and vision to achieve tangible outcomes in education, research and development in the rich, diverse European Food Culture and Know-how.
* To provide expert knowledge demonstrating that food science and technology are crucial to ensure a sustainable provision of quality food for a growing world population.
* To engage all food professionals to share their creativity, to attain innovative solutions for sustainable food systems.

**Our Aims -** EFFoST will lead efforts to provide available safe, healthy and appealing food in a sustainable manner.This will be achieved by:

* Providing a credible, independent and recognised European Exchange Platform (EEP) for food professionals.
* Interacting and forming alliances with all related disciplines and bodies in food and associated sectors to efficiently speed up the required transitions in the food area.
* Addressing the needs of professionals, including training and job opportunities for young scientists, supporting innovation pathways for enterprises including especially SMEs.
* Sharing European food processing and manufacturing practices, building on the rich and diverse European food cultures.
* Providing European consumer organisations and policy makers with transparent and clear expert knowledge on the science and technology of food.

**Governance**

EFFoST's activities are run through a non-profit foundation, which was established in June 1999 under the laws of the Netherlands. The foundation is governed by the Board. The Board consists of the President, President-Elect, General Secretary, Treasurer and Past-President and has received delegated powers from the General Assembly. EFFoST also has a number of Standing committees (SC) that focus on specific topics to strengthen our community.

**Standing committee on Science Dissemination and Communication**

In full cooperation with the EFFoST Office, the Standing Committee on Science Dissemination and Communication (SC-D&C) is responsible for supervising the organization of the annual EFFoST conference, as known as the EFFoST Flagship Event. This concerns the hosting of the event, the major guidelines and the preparation of communication materials.

In particular, the SC-D&C and EFFoST Office:

1. Develop and implement the selection process for future conferences and support the organisation of the annual conferences and any other affiliated EFFoST conference, including supporting to the scientific program, organising workshops within EU projects in which EFFoST is partner and dealing with specific EFFoST member demands and benefit;
2. Stimulate science creativity via specific events and communications to all Science partners in EFFoST (universities, research centres, research departments of companies, DG Research) in partnership with SC Societal challenges and international cooperation;
3. Encourage the production of one or more special issue(s) from the conference in EFFoST affiliated journals.

For more information visit the [EFFoST website](http://www.effost.org/).

# **Introducing the EFFoST International Conference**

## **2.1 Conference aim and objectives**

The EFFoST International Conference is an important scientific event that brings together researchers, scientists, technologists, engineers, policymakers, professionals, and students from various food-related disciplines, including microbiology, chemistry, physics, and engineering. Our conferences inspire the cross-pollination of new knowledge, ideas, and applications. With an inclusive multidisciplinary food science programme, we aim to be a leading forum of innovation where food professionals are exposed to new ideas from adjacent disciplines with the ambition to accelerate collaboration. Furthermore, networking opportunities are organised to enhance the possibility of collaboration within academia and synergism with industry in the quest to stimulate sustainable food innovations for the global economy and society.

The EFFoST conference is known for bringing together/showcasing a

Every year the EFFoST conference is well attended due to its comprehensive programme that covers a broad subject matter. Our conference objectives:

* To examine topics of international importance in the field of food science and
technology
* To provide a forum for the presentation of new research findings and to foster
interaction between academia, government and private sectors
* To provide an environment for persons with international interests in food science and technology that will: foster a better understanding of issues that are important to various nations of the world, facilitate the development of professional relationships and the exchange of ideas, and stimulate international cooperation in important new endeavours.
* To encourage students and recognize the invaluable contribution of individuals or organisations to food science and technology through the EFFoST Awards.
* To provide young food professionals working in academia, industry and/or start-ups the opportunity to expand their professional competencies and network in food science through the Young EFFoST Day. This is a day for young scientists by young scientists.
* To provide European projects and associations focused on food science the opportunity to disseminate their results, either as part of the scientific programme, as a special session and/or as part of the EU collaboration corner.

This 2,5-day event attracts at least 600 participants, coming from Europe (77%) and internationally (23%). See Annex I, for more information about the EFFoST conference delegates in 2017-2021. The programme consists of plenary and parallel sessions, and on the exhibit floor the poster presentations and the exhibitors can be found. For more information on this year’s EFFoST conference visit [www.effostconference.com](http://www.effostconference.com/).

## **2.2 Recent and future conferences**

EFFoST first started organising conferences to bring together experts in the field of food science and technology in 1986. In 2014, parallel sessions were introduced to the conference programme. We continue to find ways to improve the programme and the event as a whole with the help of the LOCs.

For more detailed information of the programme, theme and topics of the past nine conferences, visit the [EFFoST website](https://www.effost.org/effost%2Binternational%2Bconference/default.aspx).

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **City** | **Country** | **Attendance** |
| 12-14 November 2024 | Bruges | Belgium | n.a |
| 6-8 November 2023 | Valencia | Spain | 878 |
| 7-9 November 2022 | Dublin  | Ireland | 730 |
| 1-4 November 2021 | Lausanne | Switzerland | 649 |
| 10-12 November 2020 | Online | Online | 517 |
| 12-14 November 2019 | Rotterdam | Netherlands | 528 |
| 6-8 November 2018 | Nantes | France | 550  |
| 13-16 November 2017 | Sitges | Spain | 569 |
| 28-30 November 2016 | Vienna | Austria | 376 |
| 10-12 November 2015 | Athens | Greece | 580 |
| 25-28 November 2014 | Uppsala | Sweden | 370 |
| 12-15 November 2013 | Bologna | Italy | 313 |
| 20-23 November 2012 | Montpellier | France | 353 |
| 9-11 November 2011 | Berlin | Germany | 305 |
| 10-12 November 2010 | Dublin | Ireland | 290  |
| 11-13 November 2009 | Budapest | Hungary | 267  |
| 4-9 November 2008 | Ljubljana | Slovenia | 483 |
| 14-16 November 2007 | Lisbon | Portugal | 813  |
| 7-9 November 2006 | The Hague | The Netherlands | 98  |
| 25-28 October 2005 | Valencia | Spain | 350 |
| 27-29 October 2004 | Warsaw | Poland | 81 |
| 9-11 April 2003 | Copenhagen | Denmark | 400 |

# **Bid procedure**

The EFFoST International Conference bid procedure consists of two rounds. In the first round, applicants must complete the Expression of Interest form and submit it to info@effost.org. Those selected for the second round will be invited to submit a more detailed full proposal based on the information in this document.

The full proposal consists of two parts. Part I focusses on the scientific programme and Part II focusses on the location, conference venue options and social events. Both parts should be completed and sent in by the chair of the potential Local Organising Committee (LOC). In this second round, the EFFoST Board and Office will work together with you to ensure that the bid you submit is as strong as possible.

The selection of the EFFoST International conference 2026 will first and foremost be based on the quality and strength of the scientific application from the LOC, followed by the application of the venue and destination.

## **Overview of the bid procedure**

There are a number of steps in the bid procedure and each step has to be met in full for the proposal to be considered.

The bid procedure for the EFFoST International Conference is as followed:

1. **Expression of Interest (EoI)** – An expression of interest must be completed using the EFFoST EoI form, see Annex II. The EoI will provide a brief overview of the scientific programme, the city and the potential venue location(s). This submission should not exceed the information requested on the form and should include a floor plan of the conference venue with the room capacities. It is advised to contact your local Convention/City Marketing Bureau and/or conference venue for the information required.
2. **Selection of short-listed applications** – The EFFoST board will evaluate the submitted applications. All bidding parties will be informed whether they are invited to submit a full proposal application.
3. **Full Proposal** – The preparation of the full proposal is by invitation only. Guidelines for the full proposal are included in this document. Additional financial details will be provided to allow the bidding party to prepare a sound budget. EFFoST will evaluate and score the submitted full proposals based on a selection matrix. EFFoST will consider the following:

Part I - Quality of the scientific programme, the institution’s reputation, the calibre and experience of the proposed LOC.

Part II - This part will be led by EFFoST in collaboration with the bidding party to find a destination and venue that meets the criteria for the EFFoST International Conference, this includes conference venue(s) facilities, the available dates, international access to the city and the accommodation options.

1. **Site Visits** – a representative of EFFoST and the Professional Conference Organiser (PCO) will visit the cities and venues of the highest-ranking proposals. A report of the site visit will be prepared by the site visit attendees. The bidding city would be expected to sponsor this site visit. The site visit report will be assessed together with the full proposal.
2. **Selection**– The full proposal that includes a budget that breaks even will be submitted to the EFFoST Conference Organisation working group for evaluation who will provide recommendations to the EFFoST Board. The EFFoST Board will reach a decision during the Executive Board Meeting that will be held in September 2024. Shortly after, the selected LOC will be informed of the decision to host the 40th EFFoST International Conference. All other applicants will also be informed of the decision.
3. **Announcement** – The full public announcement of the host, theme(s), destination and specific dates will take place at the EFFoST2025 in the closing session.

*See Summary (page 5) for an overview of the deadlines and other important dates.*

## **3.2 Local Conference Committee (LOC) requirements**

The LOC is selected based on their ability to develop a well-balanced, high-quality scientific programme. When submitting the EoI, the LOC is encouraged to define the conference theme and topics that reflect the major goals of the scientific programme.

In the full proposal, the bid chair must provide information to support the following:

* Strong reputation of University or Research Centre in the field of Food Science and Technology
* Excellent scientific reputation of chairs, co-chairs and members of LOC
* Ability to develop an engaging programme
* An extensive scientific network to draw invite plenary and keynote speakers from
* Capability to attract a significant number of conference delegates
* An extensive professional network with connections to industry to attract additional sponsorship for the benefit of the wider food science community activities, such as Young EFFoST
* attractiveness as a host country for the conference delegates
* overall ability to stage the event with a cost-effective budget that breaks-even

The candidate’s track record in organizing successful conferences will be positively considered. The LOC’s activities include identifying and inviting plenary and keynote speakers and the abstract submission and review process, which in turn will determine the sessions and the oral and poster presentations. For a complete overview of the roles and responsibilities of the LOC, please refer to Annex III.

On a more practical note, a letter of support needs to be provided that is signed by an authorised representative of the applicant’s organization.

**Criteria to Bid -** Conference bids are only accepted from senior scientists in the field of food science and technology, who have attended at least one EFFoST conference in the past 5 years. This scientist must be employed by a research institute or university in Europe\* and an affiliated organisation of EFFoST. To ensure that the EFFoST conference is hosted throughout Europe, only applications will be considered from countries where the EFFoST conference has not been held for the past 5 years.

\* A University or College in the following countries: Albania, Andorra, Armenia, Austria, Azerbaijan, Belarus, Belgium, Bosnia and Herzegovina, Bulgaria, Croatia, Cyprus, Czech Republic, Denmark, Estonia, Finland, France, Georgia, Germany, Greece, Hungary, Iceland, Ireland, Israel (COST Cooperating State), Italy, Kazakhstan, Latvia, Liechtenstein, Lithuania, Luxembourg, , Malta, Moldova, Monaco, Montenegro, Netherlands, North Macedonia, Norway, Poland, Portugal, Romania, Russia, San Marino, Serbia, Slovakia, Slovenia, Spain, Sweden, Switzerland, Turkey, Ukraine, United Kingdom, Vatican City.

## **3.3 Venue and Destination requirements**

The selection of a possible destination is based on the following requirements:

**Congress Centre**: the facilities should comfortably accommodate the expected number of delegates for a plenary session, four parallel sessions (~120 pax), 2 Special Sessions (~60 pax) and have an exhibition floor that can accommodate the expected number of poster boards (~150, both sides used) and exhibitors, and also facilitate the networking among the conference delegates.

**Congress Centre – quote:** The quote provided by the Congress Centre must include the cost of the venue and all required facilities in as much detail as possible. Quotes must be provided in Euros and all tax charges must be specified.

**Accommodation** – The city should have sufficient number of rooms, in different hotel categories and at different room rates, to accommodate the (budget) requirement of early career to senior professionals.

**Transportation** – It is essential that the destination is easily accessible for delegates travelling by plane or public transport. The congress centre should also have adequate public transport connections.

**Subvention** – EFFoST appreciates any support the city can provide to the conference, either financial or in kind.

See chapters 4, 5, and 6 for a full overview of the necessary specifications for the conference, conference venue, and destination.

# **Conference Specifications**

## **4.1 Conference structure**

Each year the programme of the EFFoST International Conference consists of a number of reoccurring components, namely:

* Conference opening: The Conference chair and co-chair and the President of EFFoST open the conference. Additionally, a high-ranking official from a relevant Government institution officiates the formal opening of the conference.
* 3 - 5 plenary sessions: Each plenary session is dedicated to a cutting-edge food-related topic. Leading experts in the field are invited as plenary speakers to share the latest trends and developments.
* 4 parallel sessions: The plenary sessions are split into 4 parallel streams with sessions dedicated to the sub-themes and topics of the conference programme. Additional topics may be included based on the abstracts submitted. Usually, each session has a keynote speaker who establishes the parameters of the session and an appointed session chair to facilitate the transition of the speakers.
* 2 special sessions: Next to the 4 parallel streams that are dedicated the sub-themes and topics of the conference programme, additional streams can take place for EU projects, societies, or associations.
* Poster exhibition: EFFoST often has a large number of poster presentations that are usually exhibited in a maximum of two separate poster sessions, one session on each full conference day. The coffee breaks, lunches, and welcome reception provide ample opportunity to view the posters.
* Social events: the welcome reception and pub quiz are usually held on the first conference day, and conference dinner on the second conference day.
* Conference closing: this session includes the awards ceremony, thanking the current conference host and announcing the next conference host
* Pre- and post-conference events: EFFoST Board, Standing committee and working group meetings, Young EFFoST Day and other EU project meetings, shorts courses, scientific and technical visits to relevant academic, government, and industry institutions.
* Exhibition floor: Poster exhibition, tabletops and shell schemes for commercial exhibitors. Refreshment breaks and lunches for the delegates are preferably held on the exhibition floor. Find a full overview of the spatial requirements in chapter 5.1.

## **4.2 Conference programme**

The conference programme consists of several different elements, namely the scientific programme, special sessions, working group sessions, networking/social events and the Young EFFoST Day.  The EFFoST Conference is usually a 2,5-day event, over 3 full days. The Local Organising Committee can make adjustments to the conference programme.

**Monday – 1st Day**

 **Morning**

* Registration open
* Young EFFoST Day

**Afternoon**

* Welcome & Opening
* Plenary session
* Parallel sessions
* Welcome reception
* Annual EFFoST Pub Quiz

**Tuesday – 2nd Day**

* Parallel sessions
* Poster sessions
* Special sessions
* Conference dinner

**Wednesday – 3rd day**

* Plenary sessions
* Parallel sessions
* Poster sessions
* Special sessions
* Closure and Awards

## **4.3 Conference timing**

### **4.3.1 Frequency**

The EFFoST International Conference is held every year.

### **4.3.2 Period**

The EFFoST International Conference is usually organized in early November. When selecting the EFFoST Conference dates, the dates of competing congresses, courses and events are taken into consideration. In addition, the availability of the congress centre responding to this call is also an important consideration. Therefore, the conference can be considered to be held in the period between the last week of October and the first three weeks of November.

### **4.3.3 Duration**

The actual duration of the EFFoST International Conference is two and a half days. The conference programme usually starts on Monday afternoon and runs till approximately 18:00 on Wednesday.

Prior to the start of the conference, one additional ½ day is foreseen to set-up the exhibition space, if possible this is planned on the Monday morning. Here a number of table-tops and shell schemes will be set-up for sponsors and exhibitors, as well as poster boards to enable the academic delegates to showcase their work. Meetings of the EFFoST Board, Standing Committees and Working groups may also be held on the morning before the start of the conference.

Often other organisations and projects plan their meetings close to the EFFoST conference dates to optimize traveling times of their partners who will also attend the conference. Therefore, EFFoST may consider including these pre- and post-conference sessions and meetings to its schedule.

### **4.3.4 Important dates**

* Conference location announcement: 1 year ahead
* Call for abstracts: 9 months ahead
* Abstract submission deadline: 6 months ahead
* Final programme: 2 months ahead

Unless otherwise agreed between EFFoST and the Local Organising committee

## **4.4 Other specifications**

Official Language of the EFFoST International Conference: English

# **Conference venue requirements**

The facilities at the conference venue should comfortably accommodate the expected number of participants and have an exhibition floor that can accommodate the expected number of poster boards and exhibitors, and also facilitate the networking among the conference delegates.

The quote provided by the Congress Centre must include the cost of the venue and all required facilities in as much detail as possible. This would include information of standard technical equipment, poster boards, possible insurance costs and coverage, cost of personnel and their different qualifications, meals, security, cleaning, other legal requirements or binding agreements of exclusivity between the congress centre and suppliers must be provided in full. Quotes must be provided in the local currency and all tax and services charges per cost item must be specified.

## **5.1 Spatial requirements**

* Plenary hall: 500 – 600 seats in theatre style
* 3-4 additional rooms: minimum 120 seats in theatre or cabaret-style (parallel sessions)
* 2 rooms: 60 seats in theatre style (special sessions)
* Exhibition area (950-1450 m2), space for:
	+ Scientific poster exhibition requires 130-150 poster boards
	+ 8- 10 tabletops and shell schemes for commercial exhibitors
	+ 50m2 dedicated to EFFoST for EU Collaboration Corner and Student of the Year posters
	+ Catering (refreshment breaks and lunches)
		- If lunch is held on the exhibition floor, 1450m2 is required for standing lunch with at least 100 seats at sit-down tables
		- If only refreshment breaks are held on the exhibition floor and lunch is held in a separate space, then 1200m2 exhibition floor space is required
		- Catering to have sufficient space for approximately 400 standing meals and 100 seated meals
	+ Registration tables may also be included on the exhibition floor
* 1-2 meeting rooms: 10-12 seats, also available the day prior to the official opening of the Conference
* Speaker-ready room
* Registration area
* Air conditioning and heating if the location and season necessitate

Please provide a floor plan with the auditorium, additional rooms, exhibition area and other facilities, specifying the capacity, size and equipment.

## **5.2 Technical requirements**

Technical requirements per hall and room:

* data projector
* laptop
* lavaliere microphone
* two table microphones
* two roving microphones for questions from the audience
* lectern
* screen
* switcher
* top table
* 1 laser pointer
* A dedicated technician for each room is required for the duration of the conference.

**Other facilities:**

* Public address system
* Wi-Fi in all common areas
* Photocopying, telephone, facsimile
* Medical assistance
* Closed circuit television throughout the conference area, in case some sessions need to be held in to room due to larger audience
* Bank services

## **5.3 Catering**

Meals and drinks are provided to the conference delegates as part of their registration fee. Therefore, the conference venue should provide information regarding the different drink and meal packages they offer. If the conference venue does not have in-house catering, please provide this information from the three preferred catering agencies.

**Meals** – Lunch is provided on the two full days of the conference, usually Tuesday and Wednesday, for all conference delegates (approx. 600). Lunch can consist of a forked buffet, bagged or grab and go meal. A standing lunch is preferred that delegates can also attend the poster sessions. However, a few seated options are preferred for elderly and people with disabilities.

**Refreshment breaks** – on the first two full days of the conference there will be two refreshment breaks, in the morning and in the afternoon. On the first day, there will only be a afternoon refreshment break. These breaks should consist of coffee, tea, water and snack

**Drinks** – water will be provided in all conference rooms and halls throughout the conference.

**Welcome reception** – EFFoST may consider having the welcome reception at the conference venue. This would comprise of drinks and finger food. Participation is estimated to be 400 – 500 people.

**Other food and beverage requests** – additional refreshment break and lunch may be required for pre- and post-conference events and meetings.

Please provide menus for the above-mentioned drinks and meals.

# **Destination requirements**

Conference delegates do not only come from Europe, but from around the world to attend EFFoST conferences. In addition, the EFFoST conference attracts students and early careers as well as senior professionals. This informs the requirements for the availability of accommodation, transportation and subvention in the city. The following information can be provided by the local Convention or City Marketing Bureau.

## **6.1 Transportation**

The cost and time of travel is an important factor when delegates decided to visit any conference, therefore it is essential that the destination is easily accessible for delegates travelling by plane or train. Full details of air connections to main European cities, direct destinations, air fares and flight frequency are to be specified

The city should have adequate public transport infrastructure, especially between the airport, city centre and the conference venue. The conference venue should be easily accessible with public transport, as this is preferred to organising shuttle services for our delegates.

## **6.2 Accommodation**

A list with the total number of rooms available in the city per hotel category and average room rates per hotel category are to be provided by the local Convention Bureau. Most EFFoST conference delegates are academics on a limited budget therefore there should be ample accommodation options in the mid to low budget range.

A city map indicating the location of the hotels and the conference venue, plus all available methods of public transportation, must also be provided. In general, the longest distance between a hotel and the conference venue should not exceed a 30-minute journey.

If the conference venue is a hotel, delegates will book directly with the hotel from a block guaranteed by our PCO. We do not require accommodation agencies to facilitate room bookings. It is not necessary to pre-book rooms at this point of the bid procedure.

## **6.3 Social events**

Alongside our scientific programme, EFFoST also organizes a number of social events for conference delegates, such as the welcome reception and conference dinner. This is an excellent opportunity for the city to showcase its historic sites or new developments. Please provide suggestions for the conference dinner for 300 – 350 people and a welcome reception for all delegates. Should ground transportation be needed for any of the social event venues, please provide detailed information of shuttle services costs and parking facilities.

## **6.4 Subvention**

The EFFoST International Conference is expected to attract at least 600 delegates travelling from all over the world. This will give the city an economic boost as most delegates are likely to have the following expenses, 3 nights’ accommodation, meals, transport and miscellaneous. Therefore, EFFoST would appreciate any additional support that cities can provide to the conference and their delegates.

# **EFFoST Conference Management**

To ensure that the organization of the EFFoST conference is managed efficiently the following roles have been defined with corresponding responsibilities. For a more complete and detailed overview of the responsibilities of each role, see Annex III.

### **7.1 Local Organising Committee (LOC)**

The Local Organising Committee is responsible for developing a well-balanced, high-quality scientific programme to be presented at the conference. Additionally, the conference is a unique opportunity for the LOC to showcase their institution’s expertise and the developments in food science and technology in their region.

The LOC consists of a Conference Chair and several active members, who are representatives of academia, but possibly also public and private institutions. Their activities include:

* setting up the scientific committee
* inviting plenary speakers, thought leaders in the field of food science and technology
* preparing the scientific conference programme, including the oral and poster presentation sessions based on the abstract review process
* Identifying private partners as potential exhibitors/sponsors

The scientific and educational programme will strongly determine the success of the conference and therefore is a very important part of the proposal. A Memorandum of Understanding (MoU) will be signed between EFFoST and the LOC to confirm their commitment.

Refer to Annex III for the full list of responsibilities for the LOC.

### **7.2 EFFoST**

EFFoST focus is on maintaining a high scientific standard and ensuring the continuation, further development and success of the EFFoST conference in the future. The EFFoST conference creates momentum that fuels the federation throughout the year, therefore EFFoST focusses on creating opportunities to connect members and delegates. Throughout the process of organising the conference event, from the bid to the evaluation survey, the EFFoST Board and Office ensures that all activities are in line with EFFoST mission and goals.

The LOC is supported by the EFFoST Office and members of the “EFFoST Conference Organisation working group” appointed by the Standing Committee on Science Dissemination and Communication (SC-D&C) that are a repository of knowledge and experience from past conferences. EFFoST connects the LOC to relevant EFFoST members, committees and networks, enabling them to develop a high-quality scientific programme.

To ensure that objectives and targets are met, EFFoST is involved in the planning and management of the conference with the PCO and promotes the conference with a tailored communications strategy. Furthermore, the EFFoST office monitors the proper and consistent use of the EFFoST brand and safeguards its reputation and longevity.

Refer to Annex IV for the full list of responsibilities for EFFoST.

### **7.3 Scientific Committee (SC)**

The members of the Scientific Committee review abstract submissions according to the provided review criteria, process and timeline. In addition, the SC can also suggest topics and invited speakers. The members of the Scientific Committee are appointed by the LOC.

Refer to Annex V for the full list of responsibilities for the Scientific Committee.

### **7.4 Professional conference organizer (PCO)**

EFFoST will contract a Professional Conference Organiser (PCO) to oversee the administrative and logistical aspects of organising the EFFoST International Conference. The PCO is responsible for activities, such as delegate registration, abstract handling, third party contracting, communications with delegates, abstract submitters and reviewers, sponsor handling, and other practical issues.

Refer to Annex VI for the full list of responsibilities for the PCO.

### **7.5 Conference Organising Committee (COC)**

Representatives from EFFoST, the LOC and the PCO form the Conference Organising Committee (COC). In monthly meetings, current developments are discussed and opportunities to support and advise the other COC members are identified.

The COC consists of:

* + EFFoST: Jeroen Knol, Managing Director and Afroditi Karapliafi, Communications & Project Manager
	+ Local organizing committee: Chairperson and co-chair
	+ Professional Conference Organiser (PCO): conference project lead; sponsorship and sales officer, and registrations and abstract handling officer

Refer to Annex VII for the full list of responsibilities for the COC.

We hope you choose to partner with EFFoST to host the 40th EFFoST International Conference. If you have any questions regarding the bidding process, please do not hesitate to contact Afroditi Karapliafi at a.karapliafi@effost.org for more information.

# **ANNEX I – Statistics of the EFFoST conference delegates**



# **ANNEX II - Expression of Interest**

**Expression of Interest form for EFFoST2026**

Please provide the following information in a short and concise format to express your interest in hosting the 40th EFFoST International Conference. A more comprehensive overview of this information is required in the second round of the bid process. Send your Expression of Interest to Gabriela Versteeg at info@effost.org

**Part I – Scientific programme**

**Hosting Organisation details**

Name:

Organisation type: (university or research institute)

Department: (if applicable)

Address:

Telephone:

Website:

History and composition: *(include number of industry, academics, students and researchers employed or member of the organisation, 100 words max)*

Indicate scientific quality:

**Chair details**

Name:

E-mail:

Telephone number:

Employer:

Previous conference organization experience: *(include topics, highlights and number of days, sessions, participants for each event)*

**Co-chair details**

Name

E-mail

Telephone number:

Employer:

Previous conference organization experience: *(include topics, highlights and number of days, sessions, participants for each event)*

**Local Organising Committee**

Please provide the following information for each committee member that has committed to serve on the Local Organising Committee.

Name:

Affiliation:

Email:

**Proposed theme and topics**

Please provide a short introduction of the scientific programme

Conference theme:

Conference topics: (max 6)

Plenary sessions: (min 3)

Plenary speakers: (min 5)

Other highlights: (max 100 words)

**Motivation**

Please provide information on how scientific quality, expertise, experience and calibre of your organisation will contribute to the success of the EFFoST International Conference *(approx. 300 words).*

**Part II – Location and facilities**

Please contact your national tourist board, destination (city) marketing organisation and/or convention bureau as they can be a great source of information and support for your proposal.

**Proposed two Conference venues**

Venue name

Venue address:

Venue website

Space availability: *(see space requirements in Chapter 5)*

Available dates: *(3 days in the period the last week of October to third week of November)*

**Venue contact person**

Name:

Email address:

Tel:

**National support**

Has the national tourist board, destination (city) marketing organisation and/or convention bureau offered any support to bring the EFFoST Conference to their city?

Financial support/subvention: *(such as amount per delegate)*

In-kind support: *(such as covering costs of welcome reception, conference venue, travel passes for delegates, city information)*

**International accessibility**

Please provide information on the accessibility of the city and the conference venue.

Closest International airport(s):

Distance from airport to the convention venue: (*also include public transport options)*

Comments on traveling to/in the location:

**Hotels and Accommodation**

Please indicate the number and type of accommodation with 15 minutes travel of the conference venue.

|  |  |  |  |
| --- | --- | --- | --- |
| Type of Accommodation | Number of rooms | Average room rates | Walking distance (min) |
| 5 Star hotels |  |  |  |
| 4 Star hotels |  |  |  |
| 3 Star hotels |  |  |  |
| Apartment style |  |  |  |
| Budget/backpackers |  |  |  |

**Motivation**

Please provide information on how your location is unique considering the criteria mentioned above compared to other destinations and how this will contribute to the success of the EFFoST International Conference *(approx. 300 words).*

**Submitted by authorised person**

Printed Name:

Signature:

Date:

# **ANNEX III – Roles and responsibilities of the LOC**

Financial management

* Identify subvention (financial and in-kind) opportunities
* Secure sponsorship: this may be needed to close the budget or can be used to enhance certain aspects of the conference, e.g. quality and an assortment of lunch or refreshments breaks
* Keep to budget, e.g. invited speaker expenses
* Contribute to post-conference reporting

\* The LOC does not carry any financial risk; however, they should employ their best possible efforts to keep to the budget and secure the sponsorship promised during the bidding phase. This may either be achieved by reducing the costs through in-kind support or increasing income through sponsorship.

Logistics

* Propose/Advise conference venue(s) - PCO and EFFoST will select conference venue in consultation with LOC
* Propose/Advise on social event venues, such as welcome reception and conference dinner
* Propose/Advise on entertainment
* Assist scheduling of session rooms
* Support local arrangements for the program

Scientific programme

* Select conference theme and topics in consultation with SC-D&C
* Develop conference programme in consultation with SC-D&C
* Develop plenary and parallel sessions based on accepted abstracts
* Identify plenary and invited speakers and discuss with COC
* Invite plenary and invited speakers to participate
* Extend new invites if there are any gaps in the programme
* Provide PCO with contact details of invited speakers for administrative purposes
* Develop sessions (length, number and timing) based on the abstract review process
* Nominate chairs and keynote speakers for each session, often includes Scientific Committee members and invited speakers
* Deal with any scientific programme issues such as speaker replacements in case of withdrawals
* Secure the presence of a high-ranking official from a relevant Government institution to officiate the formal opening of the conference
* Invitation to national societies
* Ensure milestones and deadlines are maintained
* Chair or LOC member to be a guest editor for one or more of the supporting journals of the 40th EFFoST International Conference. During the conference programme design phase, the LOC will suggest topics for the special issue(s) and make a shortlist of potential contributors. After the conference, in agreement with the publisher and editors, invitations and call for applications will be sent out by the LOC.

Abstract management

* Define categories to be used in the abstract submission system. These differ from the sub-themes and topics described on promotional material, as these topics are not mutually exclusive making it difficult for the abstract submitters to choose and for the LOC to build a programme. The food science disciplines should be used as categories on the abstract submission form. This information is also used by the EFFoST for the planning of future conferences.
* Provide instructions for abstract submitters to PCO (e.g. defining topics)
* Respond to submission-related inquiries
* Invite experts of the programme topics to join the Scientific Committee
* Ensure active EFFoST members (including EFFoST Board and Standing Committee members) are invited to the Scientific Committee (list of past SC provided by EFFoST)
* Provide a list of Scientific Committee members and deadlines to COC for discussion
* Develop abstract review criteria and processes, based on past conferences and in consultation with SC-D&C
* Provide instructions for abstract review for the scientific committee
* Ensure that all abstracts are reviewed twice
* Select oral presenters from submitted abstracts
* Select poster presenters from submitted abstracts
* Shortlist which poster presentations could be bumped up to oral presentation, if needed
* Cluster poster presentations by sub-theme for on the exhibition floor
* Provide a list of accepted (oral, poster, oral/poster) and rejected abstract submissions to PCO who will send out notifications.

Sponsorship and Exhibitor management

* Best endeavour to achieve sponsorship to support the budget or to enhance certain aspects of the conference, e.g., quality and assortment of lunch or refreshments breaks
* Approach potential local sponsors
* Discuss potential international sponsors with EFFoST and PCO s

Communications and Marketing

* Provide information for the conference website, announcement mailings and promotional material. The text should include:
	+ Theme and topics
	+ Aim and scope
	+ Overview of the programme and sessions
	+ Target audience and the benefit to attend
	+ Call for papers
* Provide additional communication material to EFFoST e.g. description of pre, post and side events
* Present the location and theme of EFFoST2024 at the 39th EFFoST International Conference 2025
* Provide programme updates to COC for further communication
* Provide mailing lists of people potentially interested in the conference to PCO
* Distribute and share promotional material/messages in professional network, including mailing and social media posts
* Raise local awareness of the event to all relevant stakeholders and channels
* Write a welcome letter for the programme booklet
* Provide logo and a short description of hosting institute(s) (approximately 120 words) for website and printed material
* Provide name, affiliation, and photo of LOC members on the conference website and the conference booklet

At the conference

* Officiate opening and closing of the conference together with the EFFoST President. EFFoST will provide a draft PPT for these presentations with info and statistics on the conference branding
* Welcome high-ranking governmental officials invited to officiate the formal opening of the conference
* Welcome plenary and invited speakers
* Replace any last-minute absentee speakers and session chairs and reorganize timeslots if needed
* Ensure session chairs are briefed and keep to the scheduled programme
* Provide 12 students-volunteers who will support registration activities and the sessions

Post-Conference

* Contribute to the post-conference reporting

# **ANNEX IV – Roles and responsibilities of EFFoST**

Financial management

* Approve budget
* Set registration fee at an appropriate level: covering costs and accessible for as many people as possible
* Deciding the conference location based on costs

Logistics

* Determine conference location with LOC and PCO
* Determine social event venue with LOC and PCO
* Determine catering with LOC and PCO
* Plan conference space, including room set-up and exhibition floor in consultation with LOC and PCO
* Organise Student of the Year, Science to Society and Lifetime achievement awards
* Facilitate meetings: EFFoST Board, standing committees, working groups, General Assembly etc
* Coordination EU Collaboration Corner for EU projects and European Societies
* Organising special sessions (projects and associations) in consultation with LOC

Scientific Programme

* Provide guidance and access to past conference documentation for the programme timing and set-up to ensure that all conference elements are given sufficient space
* Provide lists of scientific committee members of past conferences, to ensure that active EFFoST Members at included in SC
* Connect LOC with the publisher of the EFFoST affiliated journal
* Connect the LOC with the EFFoST Standing Committee 'Dissemination and Communication' (SC-D&C)
* SC-D&C will advise the LOC on the Scientific Programme and provide knowledge and experience of past EFFoST conferences to LOC

Conference Programme

* Organise Student of the Year, Science to Society and Lifetime Achievement awards
* Facilitate meetings: EFFoST Board, Standing Committees, Working Groups, General Assembly, etc.
* Coordination EU Collaboration Corner for EU Projects and European Societies
* Organising special sessions (projects and associations) in consultation with LOC
* Support the organisers of the Young EFFoST Day

Abstract management

* Promote the abstract submission deadline on EFFoST website, social media, and with mailings to past conference delegates
* Approve all emails that are to be sent out by PCO to abstracts submitters, and oral and poster presenters

Delegate registration

* Determine reduced fees for special delegates, in consultation with LOC and PCO
* Provide information to PCO of usual processes
* Approve all emails that are to be sent out by PCO to delegates

Sponsorship and Exhibition Management

* Create prospectus with sponsor opportunities and packages in collaboration with the PCO
* Approve tailored sponsorship packages ensuring that amount of exposure provided to the sponsor is in line with their sponsorship contribution
* Provide lists of past and potential sponsor contacts to PCO
* Maintain an overview of the acquisition of (potential) sponsors

Communications and Marketing

* Create style guide for EFFoST conference branding
* Develop promotional material according to conference branding, including flyers, website, conference booklet, conference bag and the sponsorship prospectus
* Develop and maintain conference website, that includes information on the conference theme, programme, location, committees, etc. The website will also be updated by PCO
* Send mailings to promote the EFFoST conference to a wide audience, including potential conference delegates provided by the LOC, EFFoST members, past conference delegates, and possibly purchased mailing lists. Compliance with GDPR.
* Promote conference on social media including post updates of the conference, e.g early bird, invited speakers and sessions
* Approve press releases drafted by PCO
* Guard the use of the EFFoST brand in marketing activities and promotional materials of the COC
* Approve all communication materials developed by the PCO and LOC for the EFFoST conference prior to distribution
* Collaborate with PCO communications department to strengthen reach and output
* Scale up communications efforts to promote event within the Federation, capturing momentum to strengthen and expand Federation
* Creating additional content for EFFoST: interviewing speakers, promoting special sessions etc
* Report on marketing analysis
* Liaise with third parties e.g. printing, software and shipping companies

At the Conference

* Planning opening and closing ceremony in collaboration with LOC
* Prepare PPT (template) slides for LOC for the opening and closing
* Present Student of the Year, Science to Society and Lifetime achievement awards
* Contact for the members of the EFFoST Board, Standing Committees, Working Groups, General Assembly and providing support for their meetings
* Contact for the nominees of the Student of the Year
* Facilitate the popular vote for the Student of the Year on the exhibition floor
* Promote projects and associations in the EU Collaboration corner
* Document the event through e.g photography, interviews, social media posts
* Advise the PCO and LOC
* Contact for delegates for all questions about EFFoST

Post-Conference

* Make conference materials available to conference delegates including sharing oral presentations of authors who have provided their permission and the professional photos taken at the conference.
* Capture momentum to strengthen and expand the Federation
* Send and analyse results of post-conference questionnaire to improve next conference

# **ANNEX V – Roles and responsibilities of the Scientific Committee**

* Review abstract submissions according to review criteria, process and timeline specified by the LOC.
* Suggest topics and speakers
* Promote the conference in their professional networks
* Possibly act as session chair of the parallel sessions

# **ANNEX VI – Roles and responsibilities of the PCO**

Financial management

* Budget development and financial control
* Handling invoices and payments
* Contracting conference and social venues, and other third parties
* Interim and final financial reports
* Subvention management: subsidies and financial guarantees
* Tax positioning
* Insurance
* Final audit

Logistics

* Time planning and management, keeping of deadlines
* Facilitate monthly update meeting of COC
* Conference and social event venues: quotations and contracting
* Catering and other third parties: quotations and contracting
* Audio and visual support: quotations and contracting
* Accommodation: organize block booking and release excess rooms
* Plan conference space, including room set-up and exhibition floor planning in consultation with EFFoST
* Shipment of promotional materials to conference venue

Scientific programme

* Invited speakers: Send practical information regarding presentation, location, travel policy and reimbursement of costs according to EFFoST policies
* Collect and publish programme and speakers bios, photos, etc on the website
* Coordination of speaker-ready-room onsite

Abstract management

* Receive submitted abstracts through the conference website
* Communicate with submitting authors about process
* Ensure reviewers have access to abstracts online
* Send invitations and instructions of review process developed by LOC to Scientific Committee
* Ensure that review is completed within the given time frame
* Inform abstract submitters of decision: oral presentation, poster presentation, or rejection
* Provide instruction regarding presentation and poster production
* Ensure oral and poster presenters have registered before the early bird deadline to be included in programme

Delegate registration

* Set-up of online conference delegate registration
* Communication practical issues
* Invitation letters for entry visa application
* Handling of invoicing, payments and cancellations
* Provide delegates lists to EFFoST
* Produce individual certificates of participation
* Produce name badges
* Onsite registration

Sponsorship and Exhibition Management

* Sponsor acquisition, contracting and follow up
* Prepare sponsorship opportunities and packages in collaboration with EFFoST.
* Discuss tailored sponsorship packages (benefits and exposure) with EFFoST
* Exhibitor acquisition, contracting, follow up, logistics shell scheme/table top
* Oversee booth construction, exhibition material/equipment
* Manage time and floor planning

Communication and marketing

* Publicity: write and distribute press releases
* Website: update website e.g. adding information on programme, location, committees, speakers etc
* Mailings: draft text for email updates to be sent by EFFoST to mailing lists of a wide audience that may be interested in the EFFoST conference
* Conference programme booklet: collect information from invited speakers and sponsors and coordinate printing of booklet
* Conference bags: order bags, insert sponsor flyers and distribute at the conference
* Signage: EFFoST will provide templates for digital and printed signage that is to be specified by the PCO according to the venue
* Report on marketing analysis
* Conference app
* Liaise with third parties e.g. printing, software and shipping companies

Onsite management

* Onsite coordination (present at least one day before the conference)
* Manning of the registration desk
* Registration of delegates
* Set up rooms, signage, stickering of poster presentation board
* Timekeeping e.g. ensuring breaks end on time
* Main contact point for practical questions from conference delegates and exhibitors
* Main contact point for oral and poster presenters
* Coordination of speaker-ready-room on-site
* Brief onsite student volunteers
* Handing out printed certificates

Post conference

* Finalizing payments
* Prepare final financial report
* Send out thank you emails to delegates and contributors

# **ANNEX VII – Roles and responsibilities of the COC**

Representatives from EFFoST, the LOC and the PCO form the Conference Organising Committee (COC). In monthly meetings, current developments are discussed and opportunities to support and advise the other COC members are identified.

The COC consists of:

* + EFFoST: Gabriela Versteeg, Managing Director and Afroditi Karapliafi, Project & Communication Manager
	+ Local organizing committee: Chairperson and co-chair
	+ Professional Conference Organiser (PCO): conference project lead in addition to communications officer, sponsorship and sales officer, registrations and abstract handling officer when relevant
* At the monthly catch-up, the COC will provide information of developments and milestones achieved.

# **Glossary**

|  |  |
| --- | --- |
| COC: | Conference Organising Committee |
| EoI:  | Expression of Interest |
| EFFoST:  | The European Federation of Food Science and Technology |
| FP:  | Full proposal |
| Invited speakers:  | speakers of which the travel and accommodation is covered, usually the plenary speakers and a few of the keynote speakers |
| LOC: | Local Organizing Committee |
| Keynote speaker: | Invited speaker for a parallel session |
| PCO: | Professional conference organiser |
| Plenary speaker: | Invited speaker who is a highly international renowned speaker for the plenary session |
| SC: | Scientific Committee |
| SC-D&C: | Standing Committee on Dissemination and Communication  |